## Time Estimates
# | Item | Min Hours | Max Hours | Notes
1 | Submit button + Beatbuddy general 'prefer canonical' rule | 0.5 | 1 | General rule benefits many pedals
2 | Rename 'Sell Price' to 'Sug List Price' | 0.5 | 1 | UI + downloads + DB references
3 | Make/Model split (Input Make, Input Model, Make On DB, Model On DB) | 2 | 4 | Parse model from title; works in 95%+ of cases
4 | Confirm Reverb link (already done, just verify) | 0.25 | 0.5 | Goes to /p/<slug>#price-guide
5 | OneDrive integration (OAuth + sync + webhooks + daily live listings) | 18 | 25 | Microsoft Graph API; spreadsheet-first lookup
6 | Offer download redesign (2-col tier format, white background) | 2 | 4 | Restructure XLSX layout
7 | 'Custom Offer' column (per-customer override) | 2 | 4 | Temporary per-customer buy price
8 | GHL text-message integration with offer image | 6 | 10 | LeadConnector API + duplicate detection + image attach
9 | AI agent for pedals from images and texts | 20 | 30 | Claude Vision + GHL conversation parsing + dashboard
10 | Mobile app (iOS + Android with React Native, project list, search, sort) | 60 | 100 | Single codebase via React Native
11 | New column layout + edit popups + dual-section results + 'Add Pedal to DB' workflow | 8 | 12 | Major UI restructure (replaces old 5D and 5E)
12 | Multi-person upload from spreadsheet (one or many lists) | 3 | 5 | Person row + pedals; blank rows separate
13 | Field mapping clarification (covered in #11) | 0 | 0 | No additional work
14 | Excel-style compact UI for results | 3 | 6 | Dense grid layout for more visible at once
15 | Faster page load + DNS records for stompboxpricing | 1 | 2 | Drop redirect; provide DNS A/CNAME records
16 | Show price even after expiration date passes | 1 | 2 | Expiration is informational only, not gating
| Subtotal — Pricing tool (items 1-9, 11-16) | 67.25 | 106.5
| Subtotal — Mobile app (item 10) | 60 | 100
| GRAND TOTAL | 127.25 | 206.5 | hours
Separate one-time task: 18,000-pedal deduplication
| Process the spreadsheet with the matcher + Claude as backup. Returns a file with each unique pedal in col A and its variants in cols to the right. | 6 | 10 | depends on data quality

## Suggested Phasing
Phase | Items | Min Hours | Max Hours
Phase 1 — Quick wins | 1, 2, 3, 4, 6, 7, 14, 15, 16 | 12.5 | 24.5
Phase 2 — Spreadsheet integration | 5, 11, 12, 13 | 29 | 42
Phase 3 — GHL text integration | 8 | 6 | 10
Phase 4 — AI agent | 9 | 20 | 30
Separate — Mobile app | 10 | 60 | 100